## Slide 1
Redshift Shutdown
Phased Consumer Cutover
Data Platform Team | September 2026

## Slide 2
Current State: Cluster
5 x ra3.16xl
Nodes
ito-ds-redshift-dsredshift-kfbgevo589gl
43.5%
Peak CPU (hourly avg)
Room to resize to 3 nodes (~73%)
10.5%
Disk Used
RA3 managed storage -- not a constraint
123
Peak Connections
Trending down from Aug baseline
All data has been migrated to Snowflake. Redshift is no longer the source of truth.
Active users down from 36 (Aug) to 22 -- but query volume flat at ~100K/day
Automated processes dominate: Overlord, dbt, Fivetran, MV refreshes account for 99%+ of queries
Concurrency scaling already at $0 (was $8-13K/mo in Q1)
Cluster cannot be turned off until all consumers are re-pointed or disabled

## Slide 3
Current State: Daily Cost
$1,556/day
Total Daily Spend
$47,225/month | $567K annualized
Component | Daily | Monthly | Annualized | Type
Compute (5 x ra3.16xlarge) | $1,267 | $38,500 | $462,500 | Fixed until resized or terminated
Spectrum (S3 data scanned) | $149 | $4,500 | $54,400 | Variable -- drops with MV shutoff
Managed Storage (RMS) | $41 | $1,250 | $15,000 | Fixed until terminated
Snapshots | $9 | $275 | $3,300 | Fixed until deleted
Fivetran MAR (RS destination) | $90 | $2,700 | $32,400 | Variable -- drops to $0 when paused

## Slide 4
Current State: Active Consumers
The cluster stays on because these automated processes still read from it:
Consumer | Queries (7d) | Avg Daily | % of Total | Status
Overlord + MV Refreshes (datasciadmin) | 412,624 | ~47,000 | 57.7% | 52 orphaned MVs; active ones need cutover
Fivetran (service_fivetran) | 124,431 | ~39,000 | 17.4% | 8 of 18 connectors orphaned; 10 have active RS consumers
dbt Cloud (service_dbt) | 138,800 | ~19,000 | 19.4% | RS dbt models to be replaced by Snowflake models
QuickSight (service_qs_*) | 11,818 | ~9,600 | 1.7% | ECM dashboards in progress (DNA-6080)
Amplitude (service_amplitude) | 10,596 | ~1,050 | 1.5% | Evaluate consumer dependency
InfoSec (service_security) | 7,406 | ~1,000 | 1.0% | Runs until cluster off -- no action needed
Human users | ~5,500 | ~113 | <1% | 22 active, ~130 inactive (can disable)

## Slide 5
The Plan: Phased Shutdown
Phase | What | Weekly Savings | Monthly Savings | Status
1. Quick Wins | Pause 8 orphaned Fivetran connectors, stop 52 orphan MVs, disable inactive users & jobs | $735/wk | $3.2K/mo | Ready now
2. Resize 5 to 3 nodes | Elastic resize -- CloudWatch confirms safe (43.5% peak CPU) | $3,549/wk | $15.4K/mo | Ready after Phase 1
3. Consumer Cutover | Re-point remaining dbt, Overlord, and QuickSight consumers | -- | Enables 4 & 5 | In progress
4. Resize 3 to 2 nodes | After workload reduction drops peak CPU below 35% | $1,771/wk | $7.7K/mo | Blocked on Phase 3
5. Full Shutdown | Terminate cluster after 7 days at 0 queries | $4,207/wk | $18.3K/mo | Blocked on OpenAir
Phases 1 + 2 deliver $18.6K/month savings and can be executed immediately.
Critical path to full shutdown: OpenAir reverse ETL (SOX-compliant, 23 jobs, Finance sign-off).

## Slide 6
Savings Trajectory
Milestone | % Complete | Daily | Weekly | Monthly
Today (assessment done) | 16% | $0 | $0 | $0
Phase 1 executed | 37% | $105 | $735 | $3,167
Resized to 3 nodes | 70% | $612 | $4,284 | $18,567
Consumers cut over | 85% | $612 | $4,284 | $18,567
Resized to 2 nodes | 91% | $865 | $6,055 | $26,250
Full shutdown | 100% | $1,556 | $10,892 | $47,225
Every day we delay Phase 1 costs $105. Every day we delay the resize costs another $507.

## Slide 7
Assessment Findings
We inventoried every object in Redshift and classified it by activity and load mechanism:
1,136
Landing Tables
Where data first enters Redshift
970
Active Landing Tables
Have query activity in last 10 days
166
Orphaned Landing Tables
Zero consumer reads -- safe to stop
52
Orphaned MVs
Refreshing daily, nobody reading
Approach: physical read tracking
Tracked every physical table read over a 10-day window
Objects with zero consumer reads are confirmed orphans
Initial text-based analysis found ~150 orphans; physical tracking
corrected this to 52 (queries read through intermediate views)
Approach: lineage for active consumers
For active objects: Atlan lineage maps the full dependency chain
Example: mv_spectrum.workiva_workspace feeds 234 downstream objects
-- 12 direct dependents, 100 dbt models, 82 views, 9 QS datasets
This tells us what to re-point before we can turn off each pipeline

## Slide 8
Blockers & Risks
OpenAir Reverse ETL
23 bidirectional Salesforce-OpenAir sync jobs
SOX-compliant, revenue-impacting
Requires Finance/Accounting sign-off
Cross-team: CPX, BizTech, Finance
Non-prod environment provisioning delayed
FedRAMP Boundary Change
Tennessee Valley Authority is FedRAMP sponsor
Must accept removal of Redshift from FedRAMP boundary
Acceptance has not been received
Blocks full cluster termination
ECM QuickSight Dashboards
QuickSight datasets still reading from Redshift
DNA-6080 in progress (Alexandre Cerqueira)
Jira Pipeline Missing in Snowflake
No equivalent pipeline exists in Snowflake
Downstream dbt models and views depend on it
3-4 weeks to build
OpenAir, FedRAMP, and Jira block full shutdown but do NOT block the resize to 3 nodes.

## Slide 9
Timeline
Week | Milestone | Savings Impact | Owner
Sept 15-19 | Phase 1: Pause 8 Fivetran connectors, stop 52 orphan MVs, disable inactive users & Overlord jobs | $735/wk | Data Platform
Sept 22-26 | Phase 2: Resize cluster from 5 to 3 nodes | +$3,549/wk | Data Platform
Sept 22-30 | ECM QuickSight migration complete (DNA-6080) | -- | Alison Weingarten
Sept 22 - Oct 10 | Consumer cutover: map lineage, assign tickets by team, re-point consumers | -- | Data Platform + stakeholders
Oct 6-17 | Jira pipeline stood up in Snowflake | -- | Data Platform
Oct 13-31 | OpenAir reverse ETL cutover (SOX, Finance sign-off) | -- | CPX / BizTech / Finance
TBD | FedRAMP boundary change accepted by Tennessee Valley Authority | -- | Security / Compliance
Late Oct | Phase 4: Resize 3 to 2 nodes (after CPU drops below 35%) | +$1,771/wk | Data Platform
Nov 1 target | Phase 5: Terminate cluster (after 7 days at 0 queries) | +$4,207/wk | Data Platform
Target: $0 Redshift by November 1
Risks: OpenAir SOX sign-off and FedRAMP acceptance could push past October

## Slide 10
Next Steps
This week
Execute Phase 1: pause 8 orphaned Fivetran connectors, stop 52 orphan MVs,
disable 8 dormant Overlord jobs, disable ~130 inactive users
Submit cluster resize from 5 to 3 nodes
Combined impact: $612/day savings ($223K annualized)
Coming weeks
Run lineage extraction for all 843 active landing tables
Group remaining consumers by owning team
Create cutover tickets -- track progress via daily scan pipeline
Discussion
Are we aligned on the phased approach?
Who owns the resize change window?
How do we assign consumer cutover work by team?
Escalation path for OpenAir SOX dependency?